## Overview
SUMMARY
Project Overview | Detailed Report of BUG affecting the functionality of the project with respect to user requirement.
Project Name | Open Cart
Product Description | Open Cart Bug Report
Project Status | Project Type | Verification/Validation
Project Duration | Start Date | 2022-03-08 | End Date | 2022-09-23

## Report
PROJECT NAME: Open Cart |  |  |  |  | BUG SUMMARY |  | Level | User Impact |  | Business Impact |  | Status | Reviewed By
Module Name: Bug Report | [6 empty] | Critical | 80-100% |  | 80-100% |  | þ | Manager
Dependencies: Manual Test Case | [6 empty] | High | 70-80% |  | 70-80% |  | þ | Manager
Test Priority (Low/Mid/High/Highest): |  |  | High |  |  |  | Medium | 50-70% |  | 50-70% |  | þ | Manager
[7 empty] | Low | 20-50% |  | 20-50% |  | þ | Manager
BUG ID | Test Case ID | BUG Description | Steps to Find if Required | Founded Date | Reported By | Assigned To | Priority | Severity | Type | Reproducibility | Linked Issue | Status | Environment | Remarks | Attachment
OPENCART_BUG_1 | TC_RF_003 | User Registration Thank You/Successfull Mail is not received to the User | 1. Open the Application URL 2. Enter Valid details 3. Select the 'Privacy Policy' checkbox option 4. Click on 'Register' Button | 2022-03-04 | Trainee | Developer | P1(Medium) | Major |  | Everytime |  | Resolved
OPENCART_BUG_2 | TC_RF_003 | User is able to Register by providing an In-Valid Phone Number | 1. Open the Application URL 2. Enter Valid details 3. Enter In-Valid Phone Number (i.e; abcde) 4. Select 'Privacy Policy' checkbox field 5. Click on 'Register' Button | 2022-03-04 | Tester Name | Developer | P1 (Medium) | Major |  | Everytime | SW-302 | Resolved | Web Page
OPENCART_BUG_3 | TC_RF_003 | Privacy Policy' Checkbox field is not marked with red colour * symbol | 1. Open the Application URL 2. Observe the 'Privacy Policy' checkbox field is not marked with * sign | 2022-03-04 | Developer Name | Developer | P2 (Low) | Minor | Design | Everytime |  | Unresolved
OPENCART_BUG_4 | TC_RF_003 | Telephone' field is accepting the spaces and not showing warning message | 1. Open the Application URL 2. Enter spaces into all the mandatory fields including 'Telephone' field 3. Click on 'Register' Button | 2022-03-04 | Team Leader | Developer | P1 (Medium) | Major |  | Everytime |  | Resolved
OPENCART_BUG_5 | TC_RF_003 | Password' and 'Password Confirm' fields are accepting simple passwords | 1. Open the Application URL 2. Enter Valid details into all the mandatory fields 3. Enter simple password say 'abcd' into the 'Password' and 'Password Confirm' fields 4. Click on 'Register' Button | 2022-03-04 | Project Manager | Developer | P1 (Medium) | Major | Functional | Everytime | SW-380 | Resolved | Registration Page
OPENCART_BUG_6 | TC_RF_003 | Leading and Trailing spaces are accepted by the text fields in the 'Register Account' page | 1. Open the Application URL 2. Enter leading and trailing spaces to the text fields 3. Click on 'Register' Button | 2022-03-04 | Tester Name | Developer | P1 (Medium) | Minor |  | Everytime |  | Resolved
OPENCART_BUG_7 | TC_LF_001 | User is getting logged out on clicking Browser back button | 1. Open Application URL 2. Enter Valid E-Mail Address and Valid Password 3. Click on 'Login' Button 4. Click on browser back Button two times | 2022-03-04 | Developer Name | Developer | P1 (Medium) | Critical |  | Everytime | SW-389 | To Do
OPENCART_BUG_8 | TC_LF_001 | User is getting logged in automatically on clicking back button immediately after logout | 1. Login to the Application 2. Select 'Logout' option 3. Click on browser back Button | 2022-03-04 | Team Leader | Developer | P1 (Medium) | Major |  | Everytime |  | Resolved
OPENCART_BUG_9 | TC_LF_001 | Password is visible in the Page Source code | 1. Open Application URL 2. Enter password into the 'Password' field on the 'Login' page 3. Click on 'Login' button 4. Inspect the 'Password' text field | 2022-03-04 | Project Manager | Developer | P1 (Medium) | Major |  | Everytime |  | Resolved
OPENCART_BUG_10 | TC_LF_001 | User is not automatically getting logged out of the Application after 30 minutes of inactivity | 1. Login to the Application with valid credentials 2. Don't perform any action for next 30 minutes 3. After 30 minutes perform any task like Add to Cart etc. | 2022-03-04 | Tester Name | Developer | P2 (Low) | Minor |  | Everytime | SW-423 | In-Progress
OPENCART_BUG_11 | TC_LF_001 | User is not getting logged out in one browser, when logged out in another browser | 1. Login to the Application with same credentials in Chrome and Firefox Browser 2. Logout in Chrome browser 3. Check user is Logged-In in Firefox browser | 2022-03-04 | Developer Name | Developer | P2 (Low) | Minor |  | Everytime |  | Resolved
OPENCART_BUG_12 | TC_LF_001 | Email address is not getting carry forwarded from the 'Login' page to 'Forgot Your Password' page | 1. Open Application URL 2. Click on 'Forgotten Password' link | 2022-03-04 | Team Leader | Developer | P1 (Medium) | Minor |  | Everytime |  | Resolved | Application
OPENCART_BUG_13 | TC_SF_003 | Using tab keyboard key is not highlighting the 'Search in subcategories' checkbox field | 1. Open Application URL 2. Click on 'Search' icon without entering any product name 3. In the displayed 'Search' page, continuously press 'Tab' keyboard key | 2022-03-04 | Project Manager | Developer | P2 (Low) | Minor |  | Everytime |  | Resolved
OPENCART_BUG_14 | TC_RF_003 | Negative, Null and Zero values are accepted by the Qty field in Product Display Pages | 1. Open Application URL 2. Enter any Product Name say 'iMac' into the Search box field 3. Click the Product displayed in the Search results 4. Change the value to Negative or Blank or Zero in the Quantity field 5. Click on 'Add to Cart' button | 2022-03-04 | Tester Name | Developer | P0 (High) | Minor |  | Everytime |  | Resolved
OPENCART_BUG_15 | TC_RF_003 | Warning message is not displayed on updating the quantity with negative, zero or blank in the 'Shopping Cart' page | 1. Open Application URL 2. Enter 'iMac' in the Search box field 3. Click on 'Add to Cart' Button on the product displayed 4. Enter -5 into the Quantity field 5. Click on 'Update' icon option | 2022-03-04 | Developer Name | Developer | P1 (Medium) | Minor |  | Random | SW-412 | To Do
OPENCART_BUG_16 | TC_RF_003 | $8 is displayed instead of $5 in the displayed 'Estimate Shipping & Taxes' dialog | 1. Open any Application URL 2. Navigate to Shopping Cart page after adding a Product to Cart 3. Click on 'Estimate Shipping & Taxes' dialog 4. Enter 'United States' into the 'Country' text field 5. Enter 'California' into the 'Region/State' text field 6. Click on 'Get Quotes' button | 2022-03-04 | Team Leader | Developer | P0 (High) | Major |  | Everytime |  | Resolved
OPENCART_BUG_17 | TC_RF_003 | User can provide future date for the 'Order Date' field while returning the order | 1. Login to the Application 2. Click on 'Order History' Right column option 3. Click on 'View' icon option of any order displayed in the table of 'Order History' page 4. Enter any future date into the 'Order Date' field in the displayed 'Product Returns' page 5. Provide all the mandatory fields and click on 'Submit' button | 2022-03-04 | Project Manager | Developer | P1 (Medium) | Critical |  | Everytime |  | To Do | Web Page
OPENCART_BUG_18 | TC_RF_003 | Page text is not displayed in the 'About Us', 'Delivery Information', 'Privacy Policy' and 'Terms & Conditions' page | 1. Open Application URL 2. Click on 'About Us' footer option or other footer options like 'Delivery Information', 'Privacy Policy’ and 'Terms & Conditions' page | 2022-03-04 | Tester Name | Developer | P2 (Low) | Minor |  | Everytime |  | In-Progress
OPENCART_BUG_19 | TC_RF_003 | Normal User who has not registered for the Affiliate account is able to login from 'Affiliate Login section | 1. Open Application URL 2. Click on 'Affiliate' footer link 3. Login with the credentials of the normal User who has not registered for an Affiliate account 4. Click on 'Login' button | 2022-03-04 | Developer Name | Developer | P1 (Medium) | Critical |  | Everytime |  | Resolved
OPENCART_BUG_20 | TC_RF_003 | Options are not displayed in the 'Select' dropdown list of 'Iphone 12 Pro' product display page | 1. Open Application URL 2. Enter 'Iphone' text into Search text field 3. Click on the Product displayed in the Search results 4. Select any option from the 'Select' dropdown field displayed in the Product Display Page | 2022-03-04 | Team Leader | Developer | P0 (High) | Critical |  | Everytime |  | To Do
OPENCART_BUG_21 | TC_RF_003 | Logo of the Application is missing, instead 'Your Text' is getting displayed | 1. Open Application URL | 2022-03-04 | Project Manager | Developer | P0 (High) | Minor | UI/UX | Everytime |  | Resolved
OPENCART_BUG_22 | TC_RF_003 | Clicking on the first Hero image is redirecting us to a wrong Product Display Page | 1. Open Application URL 2. Click on the first Hero Image displayed in the Home page | 2022-03-04 | Team Leader | Developer | P1 (Medium) | Minor |  | Everytime |  | In-Progress
OPENCART_BUG_23 | TC_RF_003 | A blank 'Contact Us' page is displayed on submitting the form in 'Contact Us' page | 1. Open Application URL 2. Click on 'Contact Us' Option 3. Enter the details into 'Name', 'E-Mail' and 'Enquiry' fields 4. Click on 'Submit' button | 2022-03-04 | Project Manager | Developer | P0 (High) | Minor |  | Everytime |  | Resolved

## Summary
PROJECT NAME : Open Cart |  |  |  |  | Resolved Bugs |  | 2 | Version | 1.9.0
Module Name: BUG Report Summary |  |  |  |  | Unresolved Bugs |  | 1 | Date | 2022-03-04
Dependencies: Report |  |  |  |  | Open Bug |  | 2
Test Priority (Low/Mid/High/Highest): |  |  | High |  | Total no of defects |  |  |  | 5
Sr No | Bug ID | Bug Description | Priority | Severity | Impact | Status
1 | OPENCART_BUG_2 | User is able to Register by providing an In-Valid Phone Number | P1 (Medium) | Major | High | Resolved
2 | OPENCART_BUG_7 | User is getting logged out on clicking Browser back button | P1 (Medium) | Critical | Low | Unresolved
3 | OPENCART_BUG_14 | Negative, Null and Zero values are accepted by the Qty field in Product Display Pages | P0 (High) | Minor | High | Resolved
4 | OPENCART_BUG_17 | User can provide future date for the 'Order Date' field while returning the order | P1 (Medium) | Critical | Medium | Open
5 | OPENCART_BUG_22 | Clicking on the first Hero image is redirecting us to a wrong Product Display Page | P1 (Medium) | Minor | High | In-Progress